## Template Action Plan
Tasks | Responsible person | 2015-01-05 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-01-30 | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-02 | 2015-03-09 | 2015-03-16 | 2015-03-23 | 2015-03-30 | 2015-04-06 | 2015-04-13 | 2015-04-20 | 2015-04-27 | 2015-05-04 | 2015-05-11 | 2015-05-18 | Notes
Concept Note
Select a date
Draft concept note
Share with partners and get feedback
Finalize concept note with feedback
Send to donor for review
Finalize concept note
Save the Date
Draft save the date "postcard"
Draft save the date letter for key players
Draft save the date letter for broad participants
Share letter(s) with partners and get feedback
Finalize text and design email/eCard
Send letters to donor for approval
Develop list of participants to invite
Create EventBrite Registration
Send out save the date 3-6 months before the event
Branding
Select a theme
Design a logo
Vet logo and get it approved
Venue
Create selection criteria for venue
Get 3 quotes from venues
Create selection memo for venue
Develop working budget and share
Reserve room block for about 30% of guests
Pay downpayment
Reserve breakout rooms
Check on meals (breakfast, lunch, and tea)
Reserve space for before or after events
Secure multimedia for presentations (projectors, TV, etc.)
Agenda
Draft agenda shell
Share draft agenda with planning group
Finalize agenda
Print final agendas
Travel Logistics
Donor approval
Other approvals
Visa letter
Order visas
Book flights (staff)
Book flights (other presenters/participants)
Arrange ground transport to venue/hotel (deadline for registering in March 12)
Presentations
Develop list of presenters
Work with presenters to decide on KM techniques for presentations
Review and edit presentations
Collect final presentations in multiple formats
Translate presentations (if applicable) and print copies
Final Logistics
Complete materials checklist
Ship materials
Pack materials
Put together bags/folders
Evaluation
Develop event evaluation
Carry out after-action review
Communication Activities
Create promotion and dissemination plan
Create a blogging plan
Submit trip report
Finalize Share Fair report
Possible Webinar after the event

## Sample Action Plan
Tasks | Responsible person | 2015-01-05 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-01-30 | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-02 | 2015-03-09 | 2015-03-16 | 2015-03-23 | 2015-03-30 | 2015-04-06 | 2015-04-13 | 2015-04-20 | 2015-04-27 | 2015-05-04 | 2015-05-11 | 2015-05-18 | Notes
Concept Note
Select a date April 12-15, 2016 | JC | bar: 2015-01-05
Draft Concept Note | JC | bar: 2015-01-12
Share with Partners and get feedback | JC | bar: 2015-01-19 to 2015-01-26
Finalize Concept Note with Feedback | JC | bar: 2015-01-26
Send to Donor for Review | JC | bar: 2015-01-26
Finalize Concept Note | JC | bar: 2015-01-26
Save the Date
Draft Save the Date "postcard" | WG / LT | bar: 2015-02-02
Draft Save the Date letter for key players | JC / WG | bar: 2015-01-30 to 2015-02-09
Draft Save the Date letter for broad participants | JC / WG | bar: 2015-01-30 to 2015-02-09
Share letter(s) with Partners and get feedback | JC / AK | bar: 2015-01-30 to 2015-02-09
Finalize text and design email/eCard | AK | bar: 2015-02-02 to 2015-02-09
Send letters to USAID for approval | JC/MK | bar: 2015-02-09
Develop list of participants to invite | Team | bar: 2015-01-12 to 2015-02-16
Create EventBrite Registration | HF | bar: 2015-02-02
Send out Save the date by Feb. 9th (Tuesday) | HF and LA | bar: 2015-02-09
Branding
Select a theme (peer to peer sharing) | Team/Comms | bar: 2015-01-19 to 2015-01-26
Design a Logo (use similar one to original Arusha Sh Fair) | Done | bar: 2015-01-19 to 2015-01-26
Vet Logo and Get Approved | Comms | bar: 2015-02-09
Venue
Create selection criteria for venue | Done | bar: 2015-01-12
Get 3 quotes from venues | Done | bar: 2015-01-12 to 2015-01-19
Create selection memo for venue | Done | bar: 2015-01-19 to 2015-01-26
Develop working budget and share | HF | bar: 2015-01-30 to 2015-02-02
Reserve room block for about 30% of guests | Done | bar: 2015-02-02
Pay downpayment | HF | bar: 2015-02-02
Reserve breakout rooms | HF | bar: 2015-02-02
Check on Meals (Breakfast, Lunch and Tea) | HF / SD | bar: 2015-02-02
Reserve space for before or after events | HF | bar: 2015-01-30 to 2015-02-02
Secure multimedia for presentations (projectors, TV, etc.) Venue has capacity for simultaneous translation. | HF | bar: 2015-02-02
Agenda
Draft agenda shell | WG (support from JC) | bar: 2015-01-19 to 2015-02-09
Share draft agenda with planning group | WG (support from JC) | bar: 2015-02-02 to 2015-02-09
Finalize agenda including Peer Assist day | WG/Team | bar: 2015-02-16 to 2015-02-23
Print final agendas | CM | bar: 2015-04-06
Agenda: PEER ASSIST 1/2 Day Friday
Finalize Peer Assist structure | WG | bar: 2015-02-09 to 2015-02-16
Vet applicants and identify peers for the learners | WG/JC | bar: 2015-03-02 to 2015-03-16
Travel Logistics
USAID Concurrence Washington | HF | bar: 2015-02-23 to 2015-03-02
USAID Concurrence Mission | HF | bar: 2015-02-23 to 2015-03-02
Visa Letter (USAID or country sponsor) | HF | bar: 2015-02-23 to 2015-03-02
Order Visas | HF | bar: 2015-02-23 to 2015-03-02
Book flights (staff) | Individually | bar: 2015-02-23 to 2015-03-02
Book flights (other presenter/participants) | HF / Travel Agency | bar: 2015-02-23 to 2015-03-02
Arrange ground transport to venue/hotel (deadline for registering in March 12) | HF / SD | bar: 2015-03-16
Presentations
Develop list of presenters | WG (support from JC) | bar: 2015-02-02 to 2015-02-16
Work with presenters to decide on KM techniques for presentations | WG (support from JC) | bar: 2015-02-02 to 2015-03-09
Review and edit presentations | JC/WG/Comms | bar: 2015-03-30 to 2015-04-06
Collect final presentations in multiple formats | Comms | bar: 2015-03-30 to 2015-04-06
Potentially translate presentations and print off the copies | HF | bar: 2015-03-30 to 2015-04-06
Final Logistics
Complete materials checklist | Heather | bar: 2015-02-23 to 2015-03-02
Ship Materials | Heather | bar: 2015-03-02 to 2015-03-09
Pack Materials | Heather | bar: 2015-03-16 to 2015-03-23
Put together bags/folders | HF / SD | bar: 2015-03-23 to 2015-03-30
Evaluation
Develop event evaluation | WG (support from JC) | bar: 2015-03-16 to 2015-03-23
Carry out AAR | WG/JC | bar: 2015-04-20
Communication Activities
P&D Plan | Comms | bar: 2015-03-09 to 2015-03-16
Blog Plan | Comms | bar: 2015-03-09 to 2015-03-16
Trip Report | Team | bar: 2015-04-20
Share Fair Report | WG (support from JC) | bar: 2015-04-20 to 2015-05-04
Possible Webinar after the event | Team | bar: 2015-04-20 to 2015-05-04

## Share Fair Materials
Items | New or Existing? | Need to be ordered? | Quantity | Supplier | Deliver/Take | Point Person | Notes | Will these be on a table or in the bag?

## List of participants
Name | Contact Information (email/phone) | Organization | Confirmed | Point Person | Speaker? | Visa Letter Needed? | Notes

## Travel Arrangements
Attendee Name | Organization | Visa Obtained | Arrival Date, Time and Flight Number | Departure Date, Time and Flight Number | Hotel Room Confirmed | Confirmation # if available | Airport transit inbound confirmed